## Inc Matrix
Use Case | Use Case Name | Effort (People*Weeks) | Iteration 2* (3/27/18) | Iteration 3* (5/1/18)
UC 1 | Login | 1.86 | 1.86
UC 2 | Logout | 0.58 | 0.58
UC 3 | View profile | 1.86 | 1.86
UC 4 | Update Profile | 1.86 | 1.86
UC 5 | Register | 1.86 | 1.86
UC 6 | Review Registration Requests queue | 2 | 2
UC 7 | Approve Registration Request | 1.15 | 1.15
UC 8 | Reject Registration Request | 1.58 | 1.58
UC 9 | Search User Profile | 1.86 | 1.86
UC 10 | View User Profile | 1.86 | 1.86
UC 11 | Edit User Profile | 1.86 | 1.86
UC 12 | Delete Account | 1.58 | 1.58
UC 13 | View Bookings | 1.86 |  | 1.86
UC 14 /UC 25 | View event details | 1.86 |  | 1.86
UC 15/UC 26 | Cancel event | 1.86 |  | 1.86
UC 16 | Perform Estimation | 1.86 | 1.58
UC 17 | Search Available Halls | 1.86 |  | 1.86
UC 18 | Request Event | 1.58 | 1.58
UC 19 | View Catering Requests | 1.86 |  | 1.86
UC 20 | Create Catering Event | 1.86 |  | 1.86
UC 21 | Assign Resources | 1.86 |  | 1.86
UC 22 | Assign Staff | 1.86 |  | 1.86
UC 23 | Reject Catering Request | 1.86 |  | 1.86
UC 24 | View Events Schedule | 1.86 |  | 1.86
UC 27 | View Assigned events summary | 1.86 | 1.86
UC 28 | View Selected Assigned event details | 1.86 |  | 1.86
| Total Effort Estimated |  | 24.93 | 20.46
| Total Effort Available |  | 24 | 24
6
TEAM MEMBER | * Sum of the effort of each column must not exceed the ability of the team. Sum of the efforts of each row must not be less than the required effort.
Note on C31: Robb: Enter team size here